IMPLEMENTATION PLAN

Azure Agentic AI Automation

A phased roadmap to deploy AI-powered infrastructure automation

with governance, analytics, and agentic orchestration on Microsoft Azure

| Version 1.0 — Initial release | Date May 2026 |
| --- | --- |
| Audience Cloud Architecture & Engineering Leadership | Status Draft for Review |

# 1. Executive Summary

This plan outlines a structured, phased approach to deploying agentic AI automation across Azure infrastructure. The program spans four phases over 12 months, covering foundational governance, core automation agents, analytics visibility, and full-scale production rollout.

The architecture is built on three layers:

- Automation agents — specialized AI agents for FinOps, IaC generation, incident response, deployments, capacity planning, and security

- Analytics layer — Azure Monitor, Log Analytics, and Power BI / Microsoft Fabric for full observability and ROI tracking

- Governance layer — Azure Policy, RBAC, audit logging, and human-in-the-loop controls to ensure every agent action is safe and auditable

| 12 months Timeline | 4 Phases | 6 Agents | 40-60% Target ROI |  |
| --- | --- | --- | --- | --- |

# 2. Goals & Success Criteria

## 2.1 Primary Objectives

- Reduce manual cloud operations effort by 60% through AI-driven automation

- Cut infrastructure costs by 25-40% via intelligent FinOps and right-sizing agents

- Achieve sub-5-minute mean time to resolution (MTTR) for common incidents

- Enforce 100% Azure Policy compliance with zero manual remediation overhead

- Deliver real-time cost, agent performance, and compliance dashboards to leadership

## 2.2 Success Metrics

| Metric | Baseline | Target (12 months) |
| --- | --- | --- |
| Manual ops hours / month | ~200 hrs | < 80 hrs |
| Incident MTTR | 45 min avg | < 5 min avg |
| Infrastructure cost waste | ~30% of spend | < 10% of spend |
| Policy compliance rate | ~70% | 100% automated |
| Deployment failure rate | ~8% | < 2% |
| Agent action audit coverage | 0% | 100% |

# 3. Phased Implementation Roadmap

The program is broken into four 3-month phases. Each phase builds on the previous, following a Governance-first approach to ensure agents are safe to operate before scaling.

## Phase 1 — Foundation & Governance  (Months 1-3)

Establish the guardrails and infrastructure before deploying any agents. This phase is the most critical — it determines how safely the entire program runs.

| Phase 1: Foundation & Governance (Months 1-3) |  |  |
| --- | --- | --- |
| Focus area | Key activities | Outcome |
| Governance setup | Deploy Azure Policy definitions, RBAC roles, managed identities for agents, and Log Analytics workspace | All guardrails in place before any agent fires |
| AI governance | Define human-in-the-loop approval gates using Logic Apps, set responsible AI thresholds | Every destructive action requires human sign-off |
| Audit logging | Ship all events to Log Analytics + Sentinel, build baseline dashboards in Azure Monitor | Full forensic trail established |
| Hub scaffold | Deploy LLM orchestration layer (Azure OpenAI + Semantic Kernel / Prompt Flow), build agent framework | Orchestration hub ready to accept agents |
| Analytics baseline | Set up Power BI workspace connected to Log Analytics, define KPI schema | Reporting infrastructure ready |

## Phase 2 — Core Agents  (Months 4-6)

Deploy the two highest-ROI agents first — incident responder and FinOps — with governance gates active. Validate end-to-end flows before adding more agents.

| Phase 2: Core Agents (Months 4-6) |  |  |
| --- | --- | --- |
| Focus area | Key activities | Outcome |
| Incident responder | Connect Azure Monitor alerts to agent to runbook execution. Human approval for any service restart or config change | MTTR drops from 45 min to under 10 min |
| FinOps agent | Integrate Cost Management APIs, implement VM right-sizing recommendations, auto-shutdown dev resources | 10-20% cost reduction in first 60 days |
| IaC generator | Natural language to Bicep/Terraform, PR creation in Azure DevOps, policy validation before merge | IaC generation time cut by 70% |
| Analytics — Phase 2 | Live agent activity dashboard, cost savings tracker, incident resolution rate, agent success/failure rates | Real-time ROI visibility for stakeholders |

## Phase 3 — Expand Agents  (Months 7-9)

Add the remaining three agents — security, deployment, and capacity planning — now that the orchestration and governance patterns are proven.

| Phase 3: Expand Agents (Months 7-9) |  |  |
| --- | --- | --- |
| Focus area | Key activities | Outcome |
| Security agent | Continuous Defender for Cloud integration, NSG and RBAC drift detection, auto-remediation with audit trail | Policy compliance reaches 95%+ |
| Deployment agent | Azure DevOps pipeline integration, post-deploy metric monitoring, autonomous promote/rollback decisions | Deployment failure rate drops below 3% |
| Capacity planner | AKS node pool forecasting, App Service plan pre-scaling, workload prediction using Azure Monitor metrics | Zero capacity-related incidents |
| Analytics — Phase 3 | Cross-agent correlation dashboards, anomaly detection on agent behaviour, exec Power BI reports | Leadership reporting fully automated |

## Phase 4 — Production Scale & Optimise  (Months 10-12)

Harden the full system, remove remaining manual approval gates where trust is established, and optimise agent performance based on 6 months of real data.

| Phase 4: Production Scale & Optimise (Months 10-12) |  |  |
| --- | --- | --- |
| Focus area | Key activities | Outcome |
| Autonomous mode | Graduate low-risk agent actions from human-approval to auto-execute based on confidence scoring | 60% reduction in manual ops overhead achieved |
| Agent improvement loop | Feed audit log outcomes back into agent prompts, fine-tune thresholds, A/B test new reasoning strategies | Continuously improving agent accuracy |
| Fabric integration | Move analytics to Microsoft Fabric for unified data estate — Cost Management, Monitor, DevOps all in one lakehouse | Single pane of glass for all infrastructure intelligence |
| Centre of excellence | Document patterns, build internal runbooks, train ops teams, open-source reusable agent modules | Program sustainable and scalable beyond initial team |

# 4. Risks & Mitigations

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Agent takes unintended destructive action | Medium | Phase 1 governance gates, RBAC least-privilege, all actions logged; Phase 4 autonomous mode only after trust established |
| LLM hallucination in IaC generation | Medium | Azure Policy validates all generated Bicep/Terraform before PR is merged; human review required in Phase 2 |
| Cost overrun on Azure OpenAI usage | Low | Token budgets per agent, batching non-urgent tasks, monitor via Cost Management analytics |
| Team skills gap on agentic AI | High | Phase 1 includes training program; pair with Microsoft FastTrack for Azure AI |
| Audit trail gaps for compliance | Low | Log Analytics captures every tool call; Sentinel alerts on any agent action with no audit record |

# 5. Technology Stack

| Layer | Technology | Purpose |
| --- | --- | --- |
| LLM | Azure OpenAI (GPT-4o) | Core reasoning for all agents |
| Orchestration | Semantic Kernel / Prompt Flow | Agent chaining, tool use, memory |
| Automation | Azure Logic Apps, Functions | Runbook execution, approval gates |
| IaC | Bicep + Terraform, Azure DevOps | Infrastructure generation & deployment |
| Observability | Azure Monitor, App Insights | Agent telemetry, alerting |
| Analytics | Log Analytics + Power BI / Fabric | KPIs, dashboards, exec reporting |
| Governance | Azure Policy, Defender for Cloud | Guardrails, compliance, drift detection |
| Identity | Managed Identity, Azure RBAC | Least-privilege agent permissions |
| Security | Microsoft Sentinel, Key Vault | SIEM, secret management |

# 6. Immediate Next Steps

To kick off Phase 1, the following actions should be completed within the first two weeks:

- Identify executive sponsor and assign Cloud AI Program Lead

- Stand up Azure OpenAI instance in target subscription, request GPT-4o capacity

- Create Log Analytics workspace and connect all existing Azure subscriptions

- Draft initial Azure Policy definitions for agent guardrails (regions, SKUs, tags)

- Schedule Phase 1 kickoff workshop with cloud architecture and security teams

- Engage Microsoft FastTrack for Azure AI for onboarding support

Azure Agentic AI Automation — Implementation Plan  |  v1.0  |  May 2026